## Sheet1
QC Checklist for SSV Data and Data Analysis
Project Name: | Shell Shallow Hazards 2010 Multibeam measurement
= to be completed by Senior Reviewer
Step 1. Data Organization/Access
DATA | ITEM | INITIALS | DATE | NOTES
| Check access to sharepoint project site as a member including all field materials. | GW | 2010-12-01
| Collect all data and logs: GPS logs, hand-written logs, data disks with measurement and analysis files (including preliminary analysis and reports). | GW | 2010-12-01
| Check that the Field Acoustician who made the measurements has ensured that all data, analysis files and logs for all measurements are present and organized in an easily understandable manner. | GW | 2010-12-01
Step 2. SSV Field Radii Confirmation
DATA PROCESSING | ITEM | INITIALS | DATE | NOTES
| Check to see if all data was analyzed in the field and that all required results were produced (If not, describe why not in the notes cell). | no | 2010-12-07 | Waveform, spectrogram, 1/3-octave band levels, SPL vs time, and source levels were not calculated in the field report.
CALIBRATION | ITEM | INITIALS | DATE | NOTES
| Acquire blank "Quality Control - Field Study Calibration Table" spreadsheet. |  |  | No calibration was done because the recording system was the high frequency 1 MHz acquisition system
| Using field logs, locate pre- and post-deployment calibration signals within recordings. |  |  | "
| Review calibration signal in DAQview for uniformity of amplitude over the calibration period. |  |  | "
| Run Cal_gui on the cleanest 30-second window in each calibration recording (first 50Hz and then 25Hz bandwidth; if more than 0.2 dB difference ask Senior Acoustician). |  |  | "
| Record Cal_gui results from all field and lab calibrations in the Field Study Calibration Table. |  |  | "
| Compare the three SYSGAIN values and decide (with Senior Acoustician) which value to use during data analysis. |  |  | "
| Add Cal_gui output files to an appendix in the 90-day report. |  |  | "
| Upload completed Field Study Calibration Table to the appropriate Project Site. |  |  | "
| CHECK [Senior Acoustician]: Ensure SYSGAIN values used in Pulse_spl config files for 5-day report are correct. | DH | 2010-12-08
| CHECK [Senior Acoustician]: Check (if applicable) that the TC4014 sensitivity variation in frequency has been accounted for with sources greater than 300 kHz. |  |  | N/A
| CHECK [Senior Acoustician]: Review and approve Calibration Table. |  |  | N/A
NOTES - POSSIBLE CALIBRATION ISSUES | If any serial numbers are missing from the field log sheet, they can be found on the Equipment Inventory Site.
If SYSGAIN values differ by large amounts (e.g. 6dB), double-check the recorder gain settings.
ANALYSIS SPOT CHECK | ITEM | INITIALS | DATE | NOTES
| Check validity of distance files (distfiles). | GW | 2010-12-07
| Check for consistency between previous radii measured for similar airgun systems, sub-bottom profilers, and vessels in similar water depths. Check as soon as results are prepared. Example: 2008 Camden Bay Shallow Hazards sources. | GW | 2010-12-07 | Levels at the 2 farthest ranges are background. Levels at the 40m range are out of beam.
SUBMIT UPDATED RADII | ITEM | INITIALS | DATE | NOTES
| CHECK [Senior Acoustician]: Submit updated radii to client. |  |  | N/A
Step 3. High-Frequency Sources
DATA PRE-ANALYSIS | ITEM | INITIALS | DATE | NOTES
| Review all sonar data to catalogue clean parts of the spectrum (least amount of radio contamination). Do this once per deployment, not source. | GW | 2010-12-07 | 40 m range measurements are usable, farther ranges are not.
| CHECK [Senior Acoustician]: Review results of previous step with Analysis Acoustician. | DH | 2010-12-08
| Check hydrophone depth (high-frequency measurements only); in some cases vessel movement causes the hydrophone to swing up. | GW | 2010-12-08 | Checked field notes - hydrophone was at 7 m depth. No other notes to the contrary.
NOTES - HIGH FREQUENCY SOURCES | Ensure sonar source levels are processed properly. Source levels should be computed solely from the direct path signal,as opposed to level as a function of distance plots, which also include bottom surface multiples. The source signature should be characterized (pulse length, peak pressure, rms pressure) over a very short time window (typically less than a ms).* | *See example spectrogram with 6 short direct pulses, each followed by a bottom reflection with scattering.